## Gantt Chart
Emergency Shelter Allocation Platform — Project Gantt Chart (Phase 1 Prototype, Odd Semester 2026)
Course: CSS7102 ¦ Team: Sharan (Lead), Harshil Gurjar, Suhas ¦ Guide: Mr. Irfan Rajab Bhat ¦ Presidency University
# | Task | Owner | Start | End | Days | W1 03 Aug | W2 10 Aug | W3 17 Aug | W4 24 Aug | W5 31 Aug | W6 07 Sep | W7 14 Sep | W8 21 Sep | W9 28 Sep | W10 05 Oct | W11 12 Oct | W12 19 Oct | W13 26 Oct | W14 02 Nov | W15 09 Nov | W16 16 Nov | W17 23 Nov
1 | Problem study, background reading & Literature Review | All members | 2026-08-03 | 2026-08-23 | 21
2 | Requirement gathering & Architecture finalisation | All members | 2026-08-10 | 2026-08-28 | 19
3 | REVIEW 1 — Literature Review, Architecture, Expected Output, Gantt Chart | All members | 2026-08-29 | 2026-08-29 | 1 |  |  | ◆
4 | Dataset & API setup (Bhuvan, IMD, Census/WorldPop, OSM Overpass, ORS) | Harshil Gurjar | 2026-08-24 | 2026-09-06 | 14
5 | Stage 0–1: Disaster event init + Shelter discovery & suitability scoring | Harshil Gurjar | 2026-08-31 | 2026-09-13 | 14
6 | Stage 2–3: Population/demand input + Distance calculation (ORS) | Suhas | 2026-09-14 | 2026-09-27 | 14
7 | Stage 4: Optimization / allocation engine (PuLP linear program) | Sharan (Lead) | 2026-09-28 | 2026-10-11 | 14
8 | Stage 5: Persistence layer — SQLite transactional writes | Suhas | 2026-10-05 | 2026-10-18 | 14
9 | REVIEW 2 — Working prototype demo (Stages 0–5) | All members | 2026-10-17 | 2026-10-17 | 1 | [10 empty] | ◆
10 | Stage 6–7: Visualization (Folium) + Streamlit dashboard | Harshil Gurjar | 2026-10-19 | 2026-11-01 | 14
11 | Assam flood backtesting & sensitivity analysis | Sharan (Lead) | 2026-11-02 | 2026-11-08 | 7
12 | Testing, bug fixing & performance tuning | Suhas | 2026-11-09 | 2026-11-15 | 7
13 | Documentation & report writing | Sharan (Lead) | 2026-11-09 | 2026-11-22 | 14
14 | FINAL REVIEW — Full demo & submission | All members | 2026-11-28 | 2026-11-28 | 1 | [16 empty] | ◆
Legend
| Literature Review / Study |  |  | Architecture / Design |  |  | Data & API Setup |  |  | Build / Development |  |  | Testing & Validation |  |  | Documentation
◆ | Review milestone (Review 1 / Review 2 / Final Review)
Note: Review 1 is fixed at 29 Aug 2026 per the department schedule. Review 2 (17 Oct 2026) and the Final Review (28 Nov 2026) are planning assumptions on a standard Aug–Dec odd-semester calendar — update these two dates and the bars will need re-shading once your department confirms the actual dates.

## Task Details
# | Task | Owner | Start | End | Duration (days) | Key Deliverable / Exit Criterion
1 | Problem study, background reading & Literature Review | All members | 2026-08-03 | 2026-08-23 | 21 | Annotated reference list; problem statement finalised
2 | Requirement gathering & Architecture finalisation | All members | 2026-08-10 | 2026-08-28 | 19 | Finalised 8-stage pipeline + 5-layer architecture + DB schema
3 | REVIEW 1 — Literature Review, Architecture, Expected Output, Gantt Chart | All members | 2026-08-29 | 2026-08-29 | 1 | 20-mark departmental review — 4 documents presented
4 | Dataset & API setup (Bhuvan, IMD, Census/WorldPop, OSM Overpass, ORS) | Harshil Gurjar | 2026-08-24 | 2026-09-06 | 14 | Working Overpass/ORS/Bhuvan pulls for pilot district; API keys configured
5 | Stage 0–1: Disaster event init + Shelter discovery & suitability scoring | Harshil Gurjar | 2026-08-31 | 2026-09-13 | 14 | Filtered, scored, capacity-estimated shelter list in shelters table
6 | Stage 2–3: Population/demand input + Distance calculation (ORS) | Suhas | 2026-09-14 | 2026-09-27 | 14 | Distance matrix (top-N shelters/group) with ORS + haversine fallback
7 | Stage 4: Optimization / allocation engine (PuLP linear program) | Sharan (Lead) | 2026-09-28 | 2026-10-11 | 14 | PuLP model returns feasible allocation + waitlist on over-demand
8 | Stage 5: Persistence layer — SQLite transactional writes | Suhas | 2026-10-05 | 2026-10-18 | 14 | Allocations, occupancy & status updates committed transactionally
9 | REVIEW 2 — Working prototype demo (Stages 0–5) | All members | 2026-10-17 | 2026-10-17 | 1 | Departmental progress review — live demo of Stages 0–5
10 | Stage 6–7: Visualization (Folium) + Streamlit dashboard | Harshil Gurjar | 2026-10-19 | 2026-11-01 | 14 | Folium map + Streamlit UI wired to live DB reads
11 | Assam flood backtesting & sensitivity analysis | Sharan (Lead) | 2026-11-02 | 2026-11-08 | 7 | Backtest report comparing model vs. actual Assam flood shelters
12 | Testing, bug fixing & performance tuning | Suhas | 2026-11-09 | 2026-11-15 | 7 | Bug-free run across sample events; solver performance acceptable
13 | Documentation & report writing | Sharan (Lead) | 2026-11-09 | 2026-11-22 | 14 | Final project report drafted, reviewed and formatted
14 | FINAL REVIEW — Full demo & submission | All members | 2026-11-28 | 2026-11-28 | 1 | Final departmental review — full pipeline demo + report submission
| Total project span (Week 1 start → Final Review): |  |  |  | 118