Gantt Chart

Emergency Shelter Allocation Platform | Final Year Project

Proposed project schedule for the semester. The August 29, 2026 review is treated as the initial review milestone. The exact dates after the review should be aligned with the university's official project calendar.

# 1. Review Milestone

Initial Review: 29 August 2026 — Literature Review, Architecture Design, Expected Output and Gantt Chart.

# 2. Proposed 16-Week Development Plan

| Task | Start | End | Priority | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project refinement & requirements | W1 | W1 | Medium | ● |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Literature review & problem statement | W1 | W2 | Medium | ● | ● |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Architecture + database design | W1 | W2 | High | ● | ● |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OSM/Overpass data acquisition | W2 | W4 | High |  | ● | ● | ● |  |  |  |  |  |  |  |  |  |  |  |  |
| Assam flood/hazard dataset preparation | W2 | W5 | High |  | ● | ● | ● | ● |  |  |  |  |  |  |  |  |  |  |  |
| Geospatial preprocessing & shelter discovery | W4 | W7 | Medium |  |  |  | ● | ● | ● | ● |  |  |  |  |  |  |  |  |  |
| Hazard suitability scoring | W5 | W8 | High |  |  |  |  | ● | ● | ● | ● |  |  |  |  |  |  |  |  |
| Capacity estimation module | W6 | W8 | Medium |  |  |  |  |  | ● | ● | ● |  |  |  |  |  |  |  |  |
| Distance/routing module + fallback | W7 | W9 | Medium |  |  |  |  |  |  | ● | ● | ● |  |  |  |  |  |  |  |
| PuLP optimization module | W8 | W10 | High |  |  |  |  |  |  |  | ● | ● | ● |  |  |  |  |  |  |
| SQLite persistence + transactions | W9 | W10 | Medium |  |  |  |  |  |  |  |  | ● | ● |  |  |  |  |  |  |
| Folium map integration | W9 | W11 | High |  |  |  |  |  |  |  |  | ● | ● | ● |  |  |  |  |  |
| Streamlit dashboard | W10 | W13 | High |  |  |  |  |  |  |  |  |  | ● | ● | ● | ● |  |  |  |
| End-to-end integration | W12 | W14 | High |  |  |  |  |  |  |  |  |  |  |  | ● | ● | ● |  |  |
| Backtesting + sensitivity analysis | W13 | W15 | High |  |  |  |  |  |  |  |  |  |  |  |  | ● | ● | ● |  |
| Testing, bug fixing & performance | W14 | W16 | High |  |  |  |  |  |  |  |  |  |  |  |  |  | ● | ● | ● |
| Deployment / live hosting | W15 | W16 | High |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ● | ● |
| Final report & presentation | W15 | W16 | Medium |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ● | ● |

# 3. Milestones

| ID | Target | Milestone | Acceptance Criteria |
| --- | --- | --- | --- |
| M1 | 29 Aug 2026 | Initial Review | Literature Review + Architecture + Expected Output + Gantt |
| M2 | End W4 | Data Pipeline Ready | OSM/Overpass + hazard/population data can be loaded |
| M3 | End W8 | Shelter Engine Ready | Suitability + capacity estimation working |
| M4 | End W10 | Allocation Engine Ready | Distance + PuLP optimization + persistence |
| M5 | End W13 | Dashboard Alpha | End-to-end user flow available |
| M6 | End W15 | Validation Complete | Assam backtest + sensitivity analysis |
| M7 | End W16 | Final Prototype | Testing + deployment + documentation |

# 4. Critical Path

The critical dependency chain is: reliable data → shelter discovery/suitability → capacity → routing → optimization → persistence → map/dashboard → backtesting. The dashboard should not be treated as the first task; the underlying data and decision engine must work before polishing the interface.

# 5. Review-Day Gantt Explanation

The first priority is to establish a defensible problem statement and architecture.

Data acquisition and cleaning begin early because geospatial/hazard data availability can become the main project risk.

The optimization engine is developed after the shelter and demand data structures are stable.

Integration is deliberately scheduled after the individual modules are testable.

Backtesting is a separate milestone because validation is part of the project's credibility, not an optional final step.

Deployment and documentation are included before the final submission rather than left to the last day.